## Sheet1
Project Log Group #9
DATE | DESCRIPTION
2007-09-06 | Project and group assignment.
2007-09-09 | First group meeting. Went to Chili's
2007-09-10 | 1st contact with sponser. Sent email. Finished first deliverable (COC).
2007-09-11 | 1st deliverable due. Code of Conduct and Picture.
2007-09-13 | Group meeting #2. Attempted to contact sponser. Brainstormed questions to ask sponser when he returned. Discussed next deliverables. (Due 9/20)
2007-09-18 | Group meeting #3. Contacted sponser. Discussed project in detail with sponser. Contacted professor advisors. Staff meeting #1 at 4:45.
2007-09-20 | Group meeting #4. Project deliverables finished and submitted. 2pm first crash course in electromagnetic motors from Dr. Masson.
2007-09-21 | Emailed sponser basic schedule for deliverables and presentations.
2007-09-23 | Began designing project schedule using Microsoft Project.
2007-09-24 | Group Meeting #5. 2nd contact with sponser. Discussed next deliverables (Product Specs. & Scheduling
2007-09-25 | 2nd meeting with Dr. Masson and Englander. Discussed design parameters and possibilities.(Needed project specs)
2007-10-01 | Group Meeting #6. 3rd contact with sponser. Discussed specs and design possibilities. Finished up next deliverables for Thurs.
2007-10-02 | 3rd meeting with Dr. Englander. Discussed specs and design possibilites. Went over project plan.
2007-10-04 | 4th meeting with Dr. Englander and Masson. Discussed the design possibilties and constraints. Developed initial design.
2007-10-05 | Group meeting. Pro-E design and report for presentation.
2007-10-08 | 4th contact with sponsor. Dicussed conceptual design and parameters. Finished report and presentation.
2007-10-09 | Met with advisors about presentation. Finalized deliverables for Thurs. Presented.
2007-10-16 | Met with advisors to obtain access cards to CAPS building.
2007-10-17 | Contacted with advisor and sent him initial design.
2007-10-18 | Set up computer accounts in the CAPS building. Obtained key cards to CAPS.
2007-10-22 | Contacted sponser and got feedback on intital design. Talked about design methods and possible designs.
2007-10-23 | 2nd Staff meeting. Team evals. And progress report.
2007-10-25 | Began using Maxwell, a simulation program to determine design parameters.
2007-10-30 | Met with advisors about using Maxwell and presentation ideas.
2007-11-01 | Group meeting. Used Maxwell 2-D to make initial concept design and simulation.
2007-11-02 | Called sponser and discussed intial simulation and received new design characteristics
2007-11-05 | Implemented new design ideas into a base simulation model.
2007-11-06 | Met with advisors to go over presentation and simulated models.
2007-11-07 | Group meeting to make changes to simulation and design.
2007-11-08 | Presentation #2. Design Review.
2007-11-12 | Called sponser and received feedback on design and recommendations.
2007-11-13 | Made changes to design and met with advisor to check on progress and problems encountered. Staff Meeting.
2007-11-15 | Group meeting to make changes to simulation and design.
2007-11-19 | Assigned tasks for final design package and called sponser about design problems and possible solutions.
2007-11-20 | Group meeting made changes to design to figure out problems with simulation.
2007-11-26 | Group Meeting attempted to learn optimization program but failed.
2007-11-27 | Group meeting changed design and began final design anaylsis and specifics.
2007-11-28 | Called sponser about final design. Made some changes to design and came up with basis for final product.
2007-11-29 | Final Design finalized. Need adviser to check off on design. Performance simulation completed and started Thermal simulation.
2007-12-03 | Final design checked off and thermal analysis ran. Report was assembled and practiced presentation. Sent copies of report to advisors and sponser.
2007-12-04 | Final Design Presentation and Spring scope, budget and schedule turned in.
2008-12-15 | Finalized order and turned in order form for parts.
2008-01-08 | Called sponser and got him up to date with where we were at. Made comments on Final Report. Received parts.
2008-01-15 | Began machining parts for design. Sized parts and rotor.
2008-01-16 | Ordered additional parts for machining.
2008-01-17 | Machine shop. Stators and spool.
2008-01-22 | Machine shop. Re-sizing parts to fit.
2008-01-24 | Final testing devices ordered and finished fabricating.
2008-01-29 | Assembly and set up time for coil winding.
2008-01-31 | Called sponser. Met with coil winder at MagLab.
2008-02-05 | Met at MagLab to wind coil and assemble final product. Staff Meeting.
2008-02-07 | Performed thermal testing on coil.
2008-02-12 | Called Sponser and discussed progress and report
2008-02-14 | Worked on Reporting and Testing
2008-02-19 | Presentation Mid-Point Review
2008-02-21 | Machining issues. Shaft was bent and new rotor and magnets had to be ordered.
2008-02-26 | Machined new rotor and shaft with shoulder
2008-03-04 | Received magnets and reinserted into rotor for more testing
2008-03-06 | Final assembly and testing for thermal and torque
9-Mar - 16-Mar | Spring Break
2008-03-18 | Made video of actuator in action
2008-03-20 | Web Design and Called sponser. Torque measurements
2008-03-21 | Web Design and Called sponser
2008-03-25 | Presentation - Final (Walkthrough for open house)
2008-04-01 | Final Reports, Operations Manual, Website Due
2008-04-03 | OPEN HOUSE