## Sheet1
Spring Semester Gant chart
Pedibus Developement | [5 empty] | MidT pres1 |  |  |  | Spring Brk | MidT pres2 |  |  |  | Open house |  | Final Exams
| Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6 | Week #7 | Week #8 | Week #9 | Week #10 | Week #11 | Week #12 | Week #13 | Week #14 | Week #15 | Week #16 | Week #17
Task | 1/5 - 1/11 | 1/12 - 1/18 | 1/19 - 1/25 | 1/26 - 2/1 | 2/2 - 2/8 | 2/9 - 2/15 | 2/16 - 2/22 | 2/23 - 3/1 | 3/2 - 3/8 | 3/9 - 3/15 | 3/16 - 3/22 | 3/23 - 3/29 | 3/30 - 4/5 | 4/6 - 4/12 | 4/13 - 4/19 | 4/20 - 4/26 | 4/27 - 5/3
Procurement
Order Front Suspension Assy. | bar: Week #1 to Week #3
Order Aluminum | bar: Week #1 to Week #3
Order Steel | bar: Week #1 to Week #3
Order Bike parts | bar: Week #1 to Week #3
Order driveshaft, and bearings | bar: Week #1 to Week #3
Order Miscellanious parts | bar: Week #1 to Week #3
Assembly
Assemble crossmembers | bar: Week #4 to Week #5
Join rear differential and IFS | bar: Week #5 to MidT pres1 Week #6
fasten crossmembers to frame | bar: Week #5 to MidT pres1 Week #6
Assemble drive shaft w/ sprockets | bar: MidT pres1 Week #6 to MidT pres1 Week #7
Lay down flooring | bar: MidT pres1 Week #6 to MidT pres1 Week #7
Assemble uprights | bar: MidT pres1 Week #7 to MidT pres1 Week #8
Assemble bartop | bar: MidT pres1 Week #7 to MidT pres1 Week #8
Assemble driver Station | bar: MidT pres1 Week #8 to MidT pres1 Week #9
Finalize bicycle components | bar: MidT pres2 Week #12 to MidT pres2 Week #13
Wrapping up build | bar: MidT pres2 Week #13 to Open house Week #15
Other
Prepare Midterm Pres. 1 | bar: Week #5 to MidT pres1 Week #6
Prepare Midterm Pres. 2 | bar: MidT pres1 Week #9 to MidT pres2 Week #11
Prepare For open house | bar: MidT pres2 Week #14 to Open house Week #15
Study for finals | bar: Open house Week #16 to Final Exams Week #17