## Sheet1
Meetings | Description | Time (min)
General Meeting | Made introductions and threw around ideas for the competition. Discussed facebook page and group me for communication. Discussed competition rules | 30
General Meeting | Worked on code of conduct and ice breaker. | 90
Staff | Talked about competition guidelines and brought up fixed wing and multi rotor options for design. | 15
General Meeting | Gained access to portable with planes and looked at previous year's planes and components. | 60
Staff | Brought forth building multi rotor from scratch. Discussed concerns with building. | 15
General Overview | Discussed topics relating to multi rotor design and feasability. | 30
Inventory | Inventoried parts that were left in portable form previous years. | 45
Major Decision -decided on multi rotor. | Each person took turns explaining wether they wanted to go with a fixed wing or multi rotor design. Talked about benefits and negatives for each. Made a vote. Decided on multi rotor. | 120
General Meeting 10/21/2014 | New design ideas brought forth during the week about a hybrid design. Discussed benefits and negatives. Decided was best fit for competition. Discussed report. Delegated work for report. | 190
General Meeting 10/30/2014 | Worked on designs. 3 main hybrid designs were presented and evaluated. 'Modular design' was explored in more depth. | 240
General Meeting 11/2/2014 | Worked on designs further. Pros and cons of the 3 hybrid designs were finalized and it was decided that the 'modular design' was best suited for the project. | 90
General Meeting 11/4/2014 | Worked on different aspects of 'modular design'. Electrical aspects such as telemetry and autonomous control were discussed. Mechanical components such as frame, weight, motors, and power were discussed. | 90
General Meeting 11/9/2014 | Discussed motors and design plans for hybrid. Talked about cost issues and cost reduction. | 120
General Meeting 11/11/2014 | Selected motor and discussed different supporiting components such as the ESC. Started working on report. Made future plans of what to get done while waiting for parts. Researched electric components. | 150
General Meeting 11/24/2014 | Updated everyone of current progress. Discussed and finalized parts acquisition. Went over presentation and report before presentation tomorrow. | 60