## Sheet1
Meetings | Description | Time (min)
Winter Break work 12/15 | Worked on ordering parts. Figured out order forms. | 180
Genereal Meeting 1/8 | Brought everyone up to date on progress. Delegated work. Discussed build and parts. | 120
General Meeting 1/15 | Worked on report. Worked more on parts and build process. | 45
General Meeting 1/20 | Met to work on presentation and practice. After presentation discussed feedback. Made steps to execute for the next week. Delegated to the work to everyone. Discussed testing of plane and aquiring Dr. Shih's quadcopter. Talked about manufacturing process. | 180
General Meeting 1/25 | Talked about to do list. Carbon fiber rods, mounting of base plate, mounting of motors to rods, programming of audrino, parts shipped, and electrical wiring discussed. | 45
Staff 1/28 | Met with Dr. Gupta and Dr. Shih for a staff meeting. Discussed current progress (waiting for remaining parts, design issues, etc.). Talked about documented testing plans. Talked about borrowing Dr. Shih's quadcopter to do testing with. After meeting we discussed different testing apparatus and methods. We pitched ideas for different materials for the base of the plane since the current G10 is not adequate in size. Plywood was settled on tentatively. | 45
General Meeting 2/3 | We went over the parts we have received currently. Motors and wiring just came in. Discussed issues with returning parts that were incorrect. Started to put together Dr. Shih's quadcopter for testing. Quad was previously taken apart and connectors weren't connected so we spent time figuring it out. Planned on taking it to Dr. Chuy for additional help. Worked with configuring the Ardupilot. Having trouble reading sensor data from it on the computer. Discussed building the base for the plane and using plywood. | 90
General Meeting 2/16 | Worked on quadcopter. Discussed testing plans and how to execute them. Discussed progress of part fabrication. Discussed updates with meetings with various professors to help fix problems with the quadcopter. Discussed broken ardupilot, reciever not being 8 port, and broken 3DR. Attempted to meet up with Dr. Gupta and Dr. Shih. | 90
General Meeting 2/17 | Worked on presentation. Made plans to meet with professors for technical help. | 60
Prsentation 2 2/19 |  | 30
General Meeting 2/24 | Talked about updates. And made list of steps we need to take and assigned people. | 120
Staff 2/26 | Discussed midterm plans with Dr. Gupta. Updated him on progress. Talked about not continuing with dynamic scaling. Talked about what we would have ready by midterm. Asked his advice on testing. Discussed what we've learned from Senior Design. | 20
General Meeting 3/16 | Bult quad frame. Attached plane to it. Changed design to sandwich motor mounts and glue with epoxy. Discussed screws. Talked about presentaton. | 130
General Meeting 3/18 | Worked on presentation. | 60
Presentation 3/19 | Presentation day. | 30
General Meeting 3/24 | Discussed plane progress and ordering final parts. Went over budget. Talk about preparing for different deliverables. | 100
General Meeting 3/31 | Worked on deliverables. Finishing up plane build. Discussed testing plan. | 120
General Meeting 4/6 | Discussed final report and poster. Delegated report. Talked about different aspects of report. Further tested quad frame. | 90
General Meeting 4/8 | Conducted further tests over past few days. Worked through our three phase testing plan. Verified successful flights and noted procedures for proper repeatability. | 90
General Meeting 4/13 | Went over results of tests from past week. Discussed various problems that came up such as fixing control parameters. Delegated the presentation and final tasks that needed completion. | 120
Final Presentation 4/16 | Presented the final presentation. | 120
Note: Does not inculde spontaneous meetings between members or all work done by members. These were simply the scheduled meetings between the team