## Sheet1
Item No. | Task | Date Entered | Information | Decision | Action | Progress | Result | Status | Date Complete | Innolevation First Cut: Semi-finalist announced on 01/18/2018
1 | Customer Needs | 2018-09-28 | Interviewed Elderly Folk | Need to focus group with disabled community and senior citizens | Email FSU Student Disability Resource Center to focus group with disabled students | completed first iteration | None | Complete | 2018-09-21 | All Items in red are tentative assuming we move on the the next round
2 | Work Breakdown Structure | 2018-09-28 | Due: 09/21/2018 | Need to make Gant Chart or something | To be updated | completed first iteration | None | Complete | 2018-09-21
3 | VDR1 | 2018-09-28 | Due Date Pushed back to Tuesday Oct. 2 | Complete over weekend | None | None | None | Complete | 2018-09-30 | Innolevation 2nd Cut: Finalists (top 8) announced on 02/11/2018
4 | Innolevation Workshop 4: Market Research | 2018-09-29 | On 10/03/2018 @5 Innovation Hub | Attend | Attended | None | None | Complete | 2018-10-03 | All Items in purple are tentative assuming we move on the the next round
5 | VDR1 Revision | 2018-10-02 | Due: 10/04/18 | Saw Dr. Hooker 10/2/18 for Slide revision. See Meeting Minutes for changes needed | Update | None | None | Complete | 2018-10-21 | Did not make the Finals
6 | Functional Decomposition | 2018-09-28 | Basic breakdown of trash cart modules | jacob and oscar will complete | we did it | completed first iteration | waiting to hear back | Complete | 2018-09-28
7 | Innolevation Workshop 5: Triple Bottom Line - Social & Environmental Considerations | 2018-09-29 | ON 10/09/2018 @5 Innovation Hub | Attend | Attended | None | None | Complete | 2018-10-09
8 | VDR1 presentation | 2018-09-28 | Needed to push back Presentation to Monday 10/22/18 | Presentation @ 9:30 AM | None | Finished | We received great feedback from Dr. Hooker, Dr. E, Dr. Zheng, and Dr. Devine. We need to make an advisor meeting with Dr. Edrington for October | Complete | 2018-10-22
9 | Targets | 2018-09-28 | Due: Friday 10/19/18 | Need to focus group with disabled community and senior citizens | None | completed | None | Complete | 2018-10-19
10 | Innolvation Workshop 7: Prototyping & Visualizing your Product or Service | 2018-09-29 | On 10/24/2018 @5 Innovation Hub | Attend | Attended | None | None | Complete | 2018-10-24
11 | Customer Needs Resubmission | 2018-10-22 | Due: Friday 10/26/2018 | Need to focus group with FSU SDRC | Need to do Final Revision on resubmissions | Group needs to revise draft | None | Complete | 2018-10-26
12 | Pre Advisor Meeting 2 - October | 2018-10-26 | Due: 10/31/18 | Meeting with Dr. E for Wed. 10/31/2018 @ 11AM | Meeting completed | None | None | Complete | 2018-10-30
13 | Advisor Meeting October | 2018-10-26 | Due: 10/31/18 | Need to complete Concept Generation before meeting | Meeting for Wednesday 10/31/18 @ 11AM | Completed | Feedback on Targets and Concept generation | Complete | 2018-10-31
14 | Post Adviser Meeting 2 - October | 2018-10-26 | Due: 10/31/2018 | IDA needs to be updated | Adjust designs to meet advisor input | completed | Materials for project have been redefined | Complete | 2018-10-31
15 | Focus Group with the SDRC | 2018-10-26 | JR Harding: jharding@fsu.edu - Jennifer mitchell: jmitchell2@fsu.edu | Need to keep emailing and go to the SDRC | Emailed JR Harding | Has Not Responded | Will not interview SDRC | Complete | 2019-01-28
16 | Concept Generation | 2018-09-28 | Due: 10/29/2018 | Develop modularly - Need to focus group with disabled community and senior citizens |  | completed | Gone over design with Dr. Edrington at the advisor meeting | Complete | 2018-10-31
17 | Innolevation Workshop 8: Building and Marketing Your Brand | 2018-09-28 | 10/30/2018 @ 5 Innovation Hub | Attend | Attended | none | None | Complete | 2018-10-30
18 | Innolevation Stage 1 App. Deadline: Intent to Compete | 2018-09-28 | Due 11/02/2018 | None | None | None | None | Complete | 2018-09-16
19 | Concept Selection | 2018-09-28 | Due: 11/02/2018 | TBD | TBD | None | None | Complete | 2018-11-02
20 | Bill of Material | 2018-09-28 | Due: 11/09/2018 | TBD | TBD | None | None | Complete | 2018-11-09
21 | Submit VDR2 | 2018-10-26 | Due: 11/12/2018 | TBD | TBD | None | None | Complete | 2018-10-26
22 | Innolevation Workshop 9: Business Finance - Determining Costs & Revenue | 2018-09-28 | 11/14/2018 @ 5 Innovation Hub | Attend | TBD | None | Did not attend | Complete | 2018-11-14
23 | VDR2 Presentation | 2018-09-28 | "Due": 11/15/2018 | TBD | TBD | None | None | Complete | 2018-11-12
24 | Risk Assessment | 2018-09-28 | Due: 11/16/2018 | TBD | TBD | None | None | Complete | 2018-11-16
25 | Innolevation Workshop 10: Machine Intelligence | 2018-09-28 | 11/28/2018 @5 Innovation Hub | Unable to attend this workshop | did not attend | None | None | Complete | 2018-11-28
26 | Pre Advisor Meeting 3 - November | 2018-10-26 | Due: 11/30/2018 | Discuss motor and power supply calculations. Recommendations for Project Poster | Scheduled for Wed. Nov 28 @ 2PM | None | None | Complete | 2018-11-27
27 | Advisor Meeting 3 November | 2018-10-26 | Meeting Wed. Nov. 28 @ 2PM | Meeting at Dr. E's Office in CAPS | TBD | None | Need to redo torque calculations | Complete | 2018-11-28
28 | Post Adviser Meeting 3 - November | 2018-10-26 | Due: 11/30/2018 | TBD | TBD | None | None | Complete | 2018-11-28
29 | VDR3 (Poster) Submission | 2018-11-27 | Due: 12/02/2018 | Discuss with Dr. Edrington what info. to include in poster and the format we should use | Dr. E recommended using quad chart with brief bullet points and more graphics than wordy explanations. | None | None | Complete | 2018-12-02
30 | VDR3 (Poster) "Presentation" | 2018-09-28 | Due: 12/06/2018 | TBD | TBD | None | None | Complete | 2018-12-06
31 | Spring Project Plan | 2018-09-28 | Due: 12/07/2018 | TBD | TBD | None | None | Complete | 2018-12-07
32 | Sponsor Evaluation | 2018-10-26 | Due: 12/07/2018 | TBD | TBD | None | None | Complete | 2018-12-07
33 | Faculty Advisor Evaluation | 2018-10-26 | Due: 12/07/2018 | TBD | TBD | None | None | Complete | 2018-12-07
34 | Professional Photo | 2018-10-26 | Due: 12/14/18 | TBD | TBD | None | None | Complete | 2018-12-03
35 | Sponsor (Entrepreneurial) Meeting | 2018-10-26 | On 11/30/2018 @ 11AM in A231 | InNOLEvation Challenge: Discuss the Business Model Canvas with Dr Devine | Met with Dr. Devine | Completed rough draft of business model canvas | Need to create a 1 page file describing the project and submit it with our business model canvas | Complete | 2018-11-30
36 | LinkedIn Profile | 2018-10-26 | Due: 12/14/18 | TBD | TBD | None | None | Complete | 2018-12-03
37 | Innolevation STage 2 Deadline: Business Model Canvas | 2018-10-31 | Due: 01/14/2018 | TBD | TBD | None | Moved on to the next round of the Innolevation Challenge | Complete | 2019-01-14
38 | Advisor Meet & Greet | 2019-01-13 | Due: 01/11/2019 | Meeting set with Dr. E at 1PM for 01/14/2019 | TBD | completed | Need to order parts ASAP | Complete | 2019-01-14
39 | Abstract | 2019-01-14 | Due: 01/11/2019 | Completed two Abstracts | none | completed | none | Complete | 2019-01-11
40 | Abstract Resubmit | 2019-01-15 | Due: 01/18/2019 | Combine both abstracts into one | None | Completed | None | Complete | 2019-01-23
41 | Budget Update | 2019-01-16 | Due: 01/18/2019 | No purchases have been made thus far | TBD | TBD | Need to make purchases ASAP | Complete | 2019-01-18
42 | Web Master | 2019-01-17 | Due: 01/18/2019 | Oscar Flores will be web master | TBD | TBD | None | Complete | 2019-01-18
43 | Web Master Login | 2019-01-18 | Due: 01/23/2019 | None | TBD | Completed | None | Complete | 2019-01-18
44 | Post Advisor Meeting 1 | 2019-01-28 | Due: 01/31/2019 | Meeting with Dr. E scheduled for Wed. 01/30/2019 |  | TBD | Need to do tipping problems. Do not use an arc welder when welding on aluminum | Complete | 2019-01-30
45 | Team Photo | 2019-01-28 | Due: 02/01/2019 | Photo Scheduled for 10:30 AM on 01/25/2019 | TBD | Completed | None | Complete | 2019-01-25
46 | Abstract Resubmit 2 | 2019-01-28 | Due: 02/01/2019 | TBD | TBD | TBD | final draft at a reading level of 10.5 | Complete | 2019-01-31
47 | Web Page Development | 2019-01-28 | Due: 02/01/2019. Due date changed to whenever we are given access to the engineering servers | TBD | TBD | TBD | TBD | Complete | 2019-02-08
48 | InNOLEvation Presentation Preparation | 2019-01-28 | On 02/01/2019 with Dr. Devine at 2-3pm | TBD | TBD | completed the presentation slides | Need to make slides less technical and more business oriented | Complete | 2019-02-01
49 | Innolevation Workshop 11: Effective Pitches and Presentations | 2018-10-31 | 02/05/2019 @ 5 Innovation Hub | Attend | TBD | None | None | Complete | 2019-02-05
50 | Stage 3 Deadline: Final Business Model Canvas | 2018-10-31 | DUE: 02/06/2019 | TBD | TBD | Final BMC has been completed. Jacob must input the new BMC to the innolevation challenge website | None | Complete | 2019-02-04
51 | Innolevation Semi-Final Presentation Judging | 2018-10-31 | On 02/08/2019 | TBD | TBD | None | None | Complete | 2019-02-08
52 | Shark Tank Application | 2019-01-28 | Due: 02/08/2019 | TBD | TBD | None | Only need to email Devine saying we will take part in the Shark tank and who the team consists of | Complete | 2019-02-06
53 | DR5 (Senior Design Presentation) | 2019-01-28 | Due: 02/18/2019 | TBD | TBD | None | None | Complete | 2019-02-11
54 | Post Advisor Meeting 2 | 2019-01-28 | Due: 02/28/2019 | TBD | TBD | None | None | Complete | 2019-02-27
55 | Risk Assessment | 2019-01-28 | Due: 02/28/2019 | TBD | TBD | None | None | Complete | 2019-02-28
56 | Web Page Update 1 | 2019-01-28 | Due: 03/01/2019 | TBD | TBD | None | None | Complete | 2019-02-28
57 | Shark Tank Round 2 Submission | 2019-01-28 | Due: 03/08/2019 | TBD | TBD | None | None | Complete | 2019-03-03
58 | Shark Tank Preliminary Round Business Pitch | 2019-01-28 | Due: 03/08/2019 | Business Pitch is set for Monday April 1st | TBD | None | None | Complete | 2019-04-01
59 | DR6 (Senior Design Presentation) | 2019-01-28 | Due: 03/25/2019 | Scheduled for Monday April 1st at 1:30 PM | Need to reserve a room | None | None | Complete | 2019-04-01
60 | Operation Manual | 2019-01-29 | Due: 03/29/2019 | TBD | TBD | None | None | Complete | 2019-03-29
61 | Scholarship in Practice | 2019-03-25 | Due: 03/29/2019 | TBD | TBD | None | None | Complete | 2019-03-29
62 | Web Page Update 2 | 2019-01-30 | Due: 04/05/2019 | TBD | TBD | None | None | Complete | 2019-04-04
63 | Engineering Design Day | 2019-03-25 | Presentation @ 11:25-11:50 AM in CAPS 255 | Class Conflict | TBD | None | None | Complete | 2019-04-18
64 | Final Report | 2019-01-31 | Due: 04/26/2019 | TBD | TBD | None | None | Complete | 2019-04-26
65 | Prototype Demo | 2019-02-01 | Due: 04/26/2019 | Moss, Hooker, Edrington, and Devine attende. Zheng was out of town | TBD | None | None | Complete | 2019-04-26
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Sheet2
Complete
Incomplete