## Sheet1
Month Start | Milestone | Description | Start Date | End Date | Deliverable? | If Y, Deliverable Name | Completed? | Primarily Responsible | Secondary Responsible
JANUARY | New Team Schedule | Decide team's overall availability | Monday, January 7th |  | Y | Team Schedule | Y | Joe | Michael
| Ensure Bill of Materials Accuracy | Make sure all parts are listed and accounted for | Monday, January 7th | Friday, January 11th | N | --- | Y | Michael | Vincent
| Sponsor Meeting 1 |  | Friday, January 11th |  | N | --- | N | --- | ---
| Place Part Order | Place the order for the parts | Monday, January 14th |  | N | --- | N | Will | Todd
| Adviser Meeting 1 |  | Monday, January 21st |  | N | --- | N | --- | ---
FEBRUARY | 3D Print Arduino Mount | Design and print the mount for the Arduino controller | Friday, February 1st | Sunday, February 3rd | Y | Arduino Mount | N | Vincent | Todd
| Sponsor Meeting 2 |  | Friday, February 1st |  | N | --- | N | --- | ---
| Website Design | Create a website to represent our team/project | Monday, February 4th | Friday, February 8th | Y | Webiste | N | Michael | Vincent
| Obtain Parts | Receive the parts | Thursday, February 14th |  | Y | Experimental Parts | N | Todd | Joe
| Mount Gimbal | Attach the gimbal to the interior of the testing car | Friday, February 15th | Sunday, February 17th | Y | Car with Attached Gimbal Mount | N | Joe | Will
| Adviser Meeting 2 |  | Monday, February 18th |  | N | --- | N | --- | ---
| Experimental Testing 1 | Test the crash tests and body responses to low speed collisions | Friday, February 22nd | Sunday, February 24th | Y | Experimental Data | N | Michael | Joe
MARCH | Sponsor Meeting 3 |  | Friday, March 1st |  | N | --- | N | --- | ---
| Experimental Testing 2 | Follow up on crash tests if needed | Friday, March 1st | Sunday, March 3rd |  | Experimental Data | N | Michael | Joe
| MaDyMo Analysis | Take the data and obtain calculations/a general model | Monday, March 4th | Sunday, March 31st | Y | Calculations/General Empirical Model | N | Todd | Will
| Spring Break |  | Monday, March 18th | Friday, March 22nd | N | --- | N | --- | ---
| Adviser Meeting 3 |  | Monday, March 25th |  | N | --- | N | --- | ---
APRIL | Poster/PP Preparation | Begin to design the poster/final Power Point presentation | Monday, April 1st | Friday, April12th | Y | Finished Poster/Power Point | N | Michael | Joe
| Sponsor Meeting 4 |  | Friday, April 5th |  | N | --- | N | --- | ---
| Advisor Meeting 4 |  | Monday, April 8th |  | N | --- | N | --- | ---
| Sponsor Meeting 5 |  | Friday, April12th |  | N | --- | N | --- | ---
| Advisor Meeting 5 |  | Monday, April 15th |  | N | --- | N | --- | ---
| Engineering Design Day | Present our project | April 18th |  | Y | Printed Poster/Power Point | N | --- | ---
| Finals Week |  | Monday, April 29th | Friday, May 3rd | N | --- | N | --- | ---
MAY | Graduation |  | Saturday, May 4th |  | Y | Diploma | N | --- | ---
All Sponsor Meetings will be the first Friday of the month if applicable
All Adviser Meetings will be the third Monday of the month if applicable
More meeting may be schedule if the team requires assistance
Key:
Team meeting
Date of high importance
Beginning of a new month