## OPPM
Copyright OC Tanner 2007
[8 empty] | Project Instructor: Shayne McConomy |  |  |  | Project: Team 501 | [24 empty] | Date: | 2019-11-19
Project Objective: Design a device which increases the amount of recovered powder in a metal 3D printing process.
| Objectives | [7 empty] | Major Tasks |  |  | Project Completed By: April 06, 2020 | [23 empty] | Owner / Priority
[5 empty] | ✓ |  |  | 1 | Spring Semester Initial Meeting |  |  | ™ | [28 empty] | ✓
|  |  |  | ✓ |  |  |  | 2 | Spring Work Breakdown Structure |  |  |  | ™ | [27 empty] | ✓
| ✓ | [6 empty] | 3 | Apply For Graduation (Opens) |  |  |  |  | ™ | [26 empty] | ✓
[5 empty] | ✓ |  |  | 4 | Finalize General Design | [5 empty] | ™ | [25 empty] | ✓
[5 empty] | ✓ |  |  | 5 | CAD of General Design | [5 empty] | ™ | [24 empty] | ✓
|  |  |  | ✓ |  |  |  | 6 | Update Bill of Materials | [5 empty] | ™ | [21 empty] | ✓
[6 empty] | ✓ |  | 7 | Order Components | [6 empty] | ™ | [19 empty] | ✓
| ✓ | [6 empty] | 8 | Apply For Graduation (Closes) | [7 empty] | ™ | [23 empty] | ✓
[6 empty] | ✓ |  | 9 | Submit Machine Shop Request | [8 empty] | ™ | [19 empty] | ✓ | ✓
[6 empty] | ✓ |  | 10 | 3D Print Test Parts | [8 empty] | ™ | [20 empty] | ✓
[6 empty] | ✓ |  | 11 | Assemble General Design | [9 empty] | ™ | [17 empty] | ✓ | ✓
[7 empty] | ✓ | 12 | Begin General Testing | [10 empty] | ™ | [20 empty] | ✓
|  |  |  | ✓ |  |  |  | 13 | Update Sponsor | [11 empty] | ™ | [14 empty] | ✓
[5 empty] | ✓ |  |  | 14 | Begin Design Refinment and Additions | [12 empty] | ™ | [18 empty] | ✓
[5 empty] | ✓ |  |  | 15 | Finalize Updated Design | [13 empty] | ™ | [17 empty] | ✓
[5 empty] | ✓ |  |  | 16 | CAD of Updated Design | [13 empty] | ™ | [16 empty] | ✓
|  |  |  | ✓ |  |  |  | 17 | Update Bill of Materials | [13 empty] | ™ | [13 empty] | ✓
[6 empty] | ✓ |  | 18 | Order Components | [14 empty] | ™ | [11 empty] | ✓
[6 empty] | ✓ |  | 19 | Assemble and Add New Components | [15 empty] | ™ | [11 empty] | ✓ | ✓
[7 empty] | ✓ | 20 | Begin Testing New Components | [16 empty] | ™ | [14 empty] | ✓
|  |  |  | ✓ |  |  |  | 21 | Update Sponsor | [17 empty] | ™ | [8 empty] | ✓
| ✓ | [6 empty] | 22 | Spring Break (Opens) | [18 empty] | ™ | [12 empty] | ✓
| ✓ | [6 empty] | 23 | Spring Break (Closes) | [19 empty] | ™ | [11 empty] | ✓
|  |  | ✓ |  |  |  |  | 24 | Finalize Project For Presentation | [20 empty] | ™ | [10 empty] | ✓
|  |  | ✓ |  |  |  |  | 25 | Engineering Design Day | [21 empty] | ™ | [9 empty] | ✓
| ✓ | [6 empty] | 26 | Last Day of Classes | [22 empty] | ™ | [8 empty] | ✓
| ✓ | [6 empty] | 27 | Final Exam Week (Opens) | [23 empty] | ™ | [7 empty] | ✓
| ✓ | [6 empty] | 28 | Final Exam Week (Closes) | [24 empty] | ™ | [6 empty] | ✓
| ✓ | [6 empty] | 29 | Graduation | [25 empty] | ™ | [5 empty] | ✓
[10 empty] | # People working on the project: | 5
| Academic | Homework | Presentation | Documentation | Design | Assembly | Testing |  |  |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-01-22 | 2020-01-24 | 2020-01-28 | 2020-01-31 | 2020-02-03 | 2020-02-07 | 2020-02-10 | 2020-02-21 | 2020-02-26 | 2020-03-04 | 2020-03-05 | 2020-03-13 | 2020-03-16 | 2020-03-20 | 2020-04-06 | 2020-04-09 | 2020-04-24 | 2020-04-27 | 2020-05-01 | 2020-05-02 | Arlan Ohrt | Joshua Dorfman | Kevin Richter | Vincent Giannetti | Noah Tipton | All Members
Millions
[43 empty] | Budgeted | Expended
[42 empty] | Product Cost | 0 | 0
[42 empty] | Material Cost | 0 | 0
[42 empty] | Project Cost | 0 | 0
Major Tasks
Summary & Forecast
Objectives
Target Dates
Costs

## Cost Sheet
| Product Cost |  | Material Cost |  | Project Cost
Description | Budgeted | Expended | Budgeted | Expended | Budgeted | Expended |  |  |  | Salary | 20
| 500 | 0 | 1000 | 0 | 2000 | 0 |  | Millions |  | hours per week | 40
[7 empty] | Labels | Budgeted | Expended | number of weeks | 16
[7 empty] | Product Cost | 500 | 0 | Number of People | 2
[7 empty] | Material Cost | 1000 | 0 | Weight Factor | 1.75
[7 empty] | Project Cost | 2000 | 0 | Cost of Employee | 25600
Note on G3: Shayne McConomy: Cost of Employee
Note on K5: Shaynemcconomy: This is the cost of the product. You will have to calculate the material used rather than purchased

## Sheet1
Driveline Issues & Problems: |  | Today's Date: |  | 2019-11-19
| Issue: |  | How to resolve issue / What is needed: |  | Groups necessary to resolve issue: | Date Problem must be resolved:
1 | Unsure of packaging constraints for front driveline |  | Packaging plans for engine compartment |  | BIW, Engines, Energy Management, Driveline | 2009-09-25
2 | Unsure of packaging constraints for rear driveline |  | Packaging plans for driveshaft tunnel & rear sub-frame area |  | BIW, Engines, Energy Management, Suspensions, Driveline | 2009-09-25
3 | Motor specificatoins are unknown |  | Motor specifications - (We are assuming the TM4) |  | Engines, Driveline | 2009-10-01
4 | Loading parameters are unknown for rear sub-frame |  | Simpack model of rear sub-frame is needed to determine vibration constraints |  | Dr. Venhovens, Driveline | 2009-10-01
5 | Design requirements for wheels & tires are unkown |  | Need input from California School of Design about design requirements |  | Dr. Venhovens, California Design School, Driveline | 2009-10-16
Results / Resolutions:
Issue:
1 | Get in touch with BIW, Maybe using a range extender with the gearbox and generator combined
2 | Get in touch with necessary groups
3 | Assume TM$, but not set in stone
4 | Hopefully by the end of the week
5 | Plan on 17" wheels with Chevy Volt tires from Michelin