## IDA-R
Item No. | Date Entered | Information | Decision | Action | Progress | Result | Status | Date Complete
1 | 2020-09-05 | Code of Conduct | Group | Brainstorming and discussion | Writing completed, awaiting critique | Written and signed document | Complete | 2020-09-11
2 | 2020-09-06 | Basecamp invitation | Group | Tag Dr. McConomy in chat | Completed | Notifications to group members and Dr. McConomy | Complete | 2020-09-11
3 | 2020-09-07 | First meeting with sponsor | Group | Video conference | Completed | Scope, customer needs, possibly specifications | Complete | 2020-09-20
4 | 2020-09-08 | First meeting with advisor | Group | Video conference | No progress | Ideas, insight, resources | Incomplete
5 | 2020-09-09 | IDA-R | Group | Discussion | Writing completed | Excel sheet | Complete | 2020-09-13
6 | 2020-09-10 | Project Brief | Group | Discussion among group/Research | In progress | Pictures, writing, articles, internet resources | Incomplete
7 | 2020-09-10 | Project Scope | Group | Discussion with sponsor | Completed | Description, goals, markets, assumptions, and stakeholders | Complete | 2020-09-25
8 | 2020-09-10 | Customer Data | Group | Discussion with sponsor | Completed | Requirements, needs, attributes | Complete | 2010-09-25
9 | 2020-09-10 | Product Specifications | Group | Discussion with group/sponsor | In progress | Technicalities of product functions | Complete | 2021-02-19
10 | 2020-09-10 | Engineering Characteristics | Kevin Hartzog | Discussion/Research | Completed | Descriptions, visual aids, constraints | Complete | 2020-09-25
11 | 2020-09-10 | Engineering Functions | Group | Writing | Completed | Description of physical action, outcomes, system components | Complete | 2020-10-02
12 | 2020-09-10 | Targets and Metrics | Group | Data collection | Completed | Tables, charts, numbers, measures, dimensions, standards | Complete | 2020-10-30
13 | 2020-09-10 | Concept Generation | Group | Brainstorming | Completed | Ideas | Complete | 2020-11-06
14 | 2020-09-10 | Simulation | Kevin Hartzog | FEA Analysis | Completed | Graphs, visual aids | Complete | 2021-02-19
15 | 2020-09-10 | Concept Design | Group | Creative thinking | In progress | Principles | Incomplete
16 | 2020-09-10 | CAD Design | Fisher Hillburn | Geometry creation | All designs completed | Completed CAD models | Complete | 2021-02-17
17 | 2020-09-10 | Component Manufacture | Michael Corak | Ordering parts, machining | In progress | Completed parts | Incomplete
18 | 2020-09-10 | Component Testing | Michael Corak | Test design | No progress | Test data | Incomplete
19 | 2020-09-10 | System Integration | Kevin Hartzog | Assembly, fitment testing | No progress | Completed System | Incomplete
20 | 2020-09-10 | System Validation | Jordan Weid | FEA Analysis | All design analysis completed | Graphs, visual aids | Complete | 2021-02-19
21 | 2020-09-10 | System Testing | Michael Corak | Test design | No progress | Test data | Incomplete
22 | 2020-09-10 | Customer Validation | Jordan Weid/Kevin Hartzog | Discussion, testing | Advisor has validated baseline reference tool, | Performance maps, charts, graphs, visual aids | Incomplete
23 | 2020-09-10 | Technical Reports/Presentation | Group | Writing | In progress | Technical reports, manuals, PowerPoint presentations for sponsor | Incomplete | 2020-10-17
24 | 2020-10-15 | VDR1 | Group | Planning, presentation practice | Completed | Pictures, PowerPoint | Complete | 2020-10-27
25 | 2020-11-17 | VDR2 | Group | Planning, presentation practice | Completed | Pictures, PowerPoint | Complete | 2020-12-01
26 | 2020-11-20 | Bill of Materials | Group | Get quotes from suppliers, and look up prices | Completed | Excel sheet | Complete | 2020-11-24
27 | 2020-11-28 | VDR3 Poster | Kevin Hartzog | Get good pictures, create word shapes to illustrate | Completed | Poster document | Complete | 2020-12-04
28 | 2020-01-13 | Staff Meeting 1 | [5 empty] | 2021-01-28
29 | 2021-01-15 | Altered Scope | Group | Change evidence manual, update presentations | Completed | Word docs, PowerPoint docs, discussion, meeting with sponsor | Complete | 2021-01-26
30 | 2021-01-20 | DR4 | Group | Planning, presentation practice | Completed | Pictures, PowerPoint, FEA results, CAD images | Complete | 2021-01-26
31 | 2021-01-25 | Final Baseline Design | Kevin Hartzog | Creating geometry | Completed | CAD Design | Complete | 2021-02-05
32 | 2021-01-25 | Baseline Thermal Analysis | Kevin Hartzog | Developing mathematical equations, setting assumptions | Completed | Graphs, plots, pictures, excel sheet | Complete | 2021-02-07
33 | 2021-02-10 | Staff Meeting 2
34 | 2021-02-11 | Final Target Requirements | Group/Sponsor | Setting final design parameters | Completed | Metrics, dimensions, thermodynamic properties | Complete | 2021-02-20
35 | 2021-02-12 | Complex Heat Exchanger geometry design | Group | Creating more complex geometry and evaluate performance | Completed | Thermodynamic performance, CAD design, FEA results | Complete | 2021-02-25
36 | 2021-02-15 | Interface Solution at Outlet | Group | Design flange to mate to inlet of test articles | Completed | CAD geometry | Complete | 2021-03-05
37 | 2021-02-15 | Solid Temperature Analysis | Group | Analyze temperature of heat exchanger solid domain | Completed | FEA results, thermodynamic properties | Complete | 2021-03-07
38 | 2021-03-11 | Staff Meeting 3
39 | 2021-03-12 | Quote from supplier | Group | Get pricing for 3D printing final design out of tungsten | In progress | Quote, manufacturing plan | Incomplete
40 | 2021-03-12 | Method of manufacture | Group | Choose final method of manufacture | No progress | Technical report | Incomplete
41 | 2021-03-12 | Interface Solution at Inlet | Group | Choose mating to 1/2" AN female fitting | In progress | CAD design | Incomplete
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108

## Contact Log
Last Name | First Name | Full Name | email | Company | Contacted By | Date Initially Contacted | Method of First Contact | Last Contacted by | Date of Last Contact | Method of Last Contact | Information | Action | Result

## Data Validation
Complete
Incomplete