## Zenith Gantt
The Zenith Program - NASA Student Launch |  |  |  |  | Phase 1 | [32 empty] | PHASE TWO | [32 empty] | PHASE 3 | [55 empty] | PHASE 4 | [38 empty] | PHASE 5
WBS NUMBER | TASK TITLE | START DATE | END DATE | DURATION | 1 | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26 |  |  |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37
[5 empty] | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M
1 | Proposal | 2022-08-14 | 2022-10-04 | 51
1.1 | RFP Released | 2022-08-19 | 2022-08-19 | - | bar: 1 F
1.1.1 | Proposal Work | 2022-08-19 | 2022-09-19 | 31 | bar: 2 W to 6 M
1.2 | Completed Proposal Submission | 2022-09-19 | 2022-09-19 | - | bar: 6 M
1.3 | Awarded Proposals Announced | 2022-10-04 | 2022-10-04 | - | bar: 8 T
2 | PDR | 2022-10-06 | 2022-11-21 | 46
2.1 | PDR Q&A | 2022-10-06 | 2022-10-06 | 0 | bar: 8 R
2.2 | Establish Social Media Accounts | 2022-10-07 | 2022-10-07 | 0 | bar: 8 R
2.3 | Finalize Preliminary Design | 2022-09-19 |  | #NUM! | bar: 6 T to 10 W
2.4 | Write PDR Report | 2022-10-09 | 2022-10-19 | 10 | bar: 10 R to 11 F
2.5 | Create PDR Presentation | 2022-10-19 | 2022-10-25 | 6 | bar: 10 R to 12 M
2.5.1 | PDR Deadline | 2022-10-26 | 2022-10-26 | - | bar: 12 M
2.6 | PDR Video Conference | 2022-11-01 | 2022-11-21 | 20 | bar: 12 M to 15 M
3 | STEM Engagement | 2022-10-17 | 2023-02-07 | 113
4 | CDR | 2022-11-22 | 2023-02-07 | 77
4.1 | Assess PDR Feedback | 2022-11-22 | 2022-11-25 | 3 | bar: 15 T to 15 F
4.1.1 | Implement Design Improvements | 2022-11-25 | 2022-11-30 | 5 | bar: 15 F to 16 W
4.2 | CDR Q&A | 2022-12-01 | 2022-12-01 | 1 | bar: 16 R
4.3 | Manufacture Subscale Model | 2022-12-02 | 2022-12-09 | 7 | bar: 16 F to 17 F
4.4 | Write CDR Report | 2022-12-02 | 2023-01-08 | 37 | bar: 16 F to 22 F
4.5 | Subscale Model Launch Test | 2022-12-10 | 2022-12-10 | 0 | bar: 17 F
4.6 | Create CDR Presentation Slides | 2022-12-02 | 2023-01-08 | 37 | bar: 16 F to 22 F
4.6.1 | CDR Deadline | 2023-01-09 | 2023-01-09 | - | bar: 22 M
4.7 | CDR Video Conference | 2023-01-17 | 2023-02-07 | 21 | bar: 23 T to 26 T
5 | FRR and Flight Demonstration | 2023-02-09 | 2023-04-03 | 53
5.1 | FRR Q&A | 2023-02-09 | 2023-02-09 | 0 | bar: 26 R
5.2 | Manufacture Full-Scale Vehicle | 2023-02-10 | 2023-02-25 | 15 | bar: 26 F to 28 F
5.2.1 | Manufacture Payload | 2023-02-10 | 2023-02-25 | 15 | bar: 26 F to 28 F
5.2.2 | Pre-flight Testing | 2023-02-16 | 2023-03-02 | 14 | bar: 27 R to 29 R
5.3 | Vehicle Demonstration Flight | 2023-03-04 | 2023-03-04 | 1 | bar: 29 F
5.3.1 | Vehicle Demonstration Flight Deadline | 2023-03-06 | 2023-03-06 | 0 | bar: 30 M
5.4 | Write FRR Report | 2023-02-16 | 2023-03-02 | 14 | bar: 27 R to 30 M
5.5 | Create FRR Presentation Slides | 2023-02-16 | 2023-03-02 | 14 | bar: 27 R to 30 M
5.5.1 | FRR Report Deadline | 2023-03-06 | 2023-03-06 | 0 | bar: 30 M
5.6 | FRR Video Conference | 2023-03-13 | 2023-03-31 | 18 | bar: 31 M to 33 F
5.7 | Payload Demonstration Flight | 2023-04-01 | 2023-04-01 | 1 | bar: 33 F
5.7.1 | Payload Demonstration Flight Deadline | 2023-04-03 | 2023-04-03 | - | bar: 34 M
6a | Competition | 2023-04-12 | 2023-04-16 | 4
6.1 | Travel to Marshall SFC | 2023-04-12 | 2023-04-12 | 1 | bar: 34 W
6.2 | Launch Readiness Review | 2023-04-13 | 2023-04-14 | 1 | bar: 34 R to 34 F
6.3 | Launch Day | 2023-04-15 | 2023-04-15 | 1 | bar: 34 F
6.3.1 | Backup Launch Day | 2023-04-16 | 2023-04-16 | 1 | bar: 34 F
6b | PLAR | 2023-04-17 | 2023-05-01 | 14
6.4 | Analyze competition flight data | 2023-04-17 | 2023-04-19 | 2 | bar: 35 M to 35 T
6.5 | Write PLAR Report | 2023-04-19 | 2023-04-30 | 11 | bar: 35 W to 36 F
6.5.1 | PLAR Report Deadline | 2023-05-01 | 2023-05-01 | - | bar: 37 M
9/19/22 Proposal Due
10/4/22 Acceptance Announcement
10/26/22
PDR Deadline
11/21/22
PDR Video Conference End
12/01/22
CDR Q.A
12/10/22
Subscale Launch
1/9/23
CDR Deadline
2/07/23
CDR Video Conference End
3/04/23
Full Scale Demo Launch
4/03/23
Payload Demo Deadline
05/01/23
PLAR Deadline
2/9/23
FRR Q.A

## Part1
The Zenith Program - NASA Student Launch |  |  |  |  | Phase 1 | [32 empty] | PHASE TWO
WBS NUMBER | TASK TITLE | START DATE | END DATE | DURATION | 1 | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15
[5 empty] | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T
1 | Proposal | 2022-08-14 | 2022-10-04 | 51
1.1 | RFP Released | 2022-08-19 | 2022-08-19 | -
1.1.1 | Proposal Work | 2022-08-19 | 2022-09-19 | 31
1.2 | Completed Proposal Submission | 2022-09-19 | 2022-09-19 | -
1.3 | Awarded Proposals Announced | 2022-10-04 | 2022-10-04 | -
2 | PDR | 2022-10-06 | 2022-11-21 | 46
2.1 | PDR Q&A | 2022-10-06 | 2022-10-06 | 0
2.2 | Establish Social Media Accounts | 2022-10-07 | 2022-10-07 | 0
2.3 | Finalize Preliminary Design | 2022-09-19 | 2022-10-12 | 23
2.4 | Write PDR Report | 2022-10-09 | 2022-10-19 | 10
2.5 | Create PDR Presentation | 2022-10-19 | 2022-10-25 | 6
2.5.1 | PDR Deadline | 2022-10-26 | 2022-10-26 | -
2.6 | PDR Video Conference | 2022-11-01 | 2022-11-21 | 20
3 | STEM Engagement | 2022-10-17 | 2023-02-07 | 113
4 | CDR | 2022-11-22 | 2023-02-07 | 77
9/19/22 Proposal Due
10/4/22 Acceptance Announcement
10/26/22
PDR Deadline
11/9/22
PDR Video Conference End

## Part2
The Zenith Program - NASA Student Launch |  |  |  |  | Phase 3
WBS NUMBER | TASK TITLE | START DATE | END DATE | DURATION |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26
[5 empty] | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T
3 | STEM Engagement | 2022-10-17 | 2023-02-07 | 113
4 | CDR | 2022-11-22 | 2023-02-07 | 77
4.1 | Assess PDR Feedback | 2022-11-22 | 2022-11-25 | 3 | bar: T to F
4.1.1 | Implement Design Improvements | 2022-11-25 | 2022-11-30 | 5 | bar: F to 16 W
4.2 | CDR Q&A | 2022-12-01 | 2022-12-01 | 1 | bar: 16 R
4.3 | Manufacture Subscale Model | 2022-12-02 | 2022-12-09 | 7 | bar: 16 F to 17 F
4.4 | Write CDR Report | 2022-12-02 | 2023-01-08 | 37 | bar: 16 F to 22 F
4.5 | Subscale Model Launch Test | 2022-12-10 | 2022-12-10 | 0 | bar: 17 F
4.6 | Create CDR Presentation Slides | 2022-12-02 | 2023-01-08 | 37 | bar: 16 F to 22 F
4.6.1 | CDR Deadline | 2023-01-09 | 2023-01-09 | - | bar: 22 M
4.7 | CDR Video Conference | 2023-01-17 | 2023-02-07 | 21 | bar: 23 T to 26 T
5 | FRR and Flight Demonstration | 2023-02-09 | 2023-04-03 | 53
12/01/22
CDR Q.A
12/10/22
Subscale Launch
1/9/23
CDR Deadline
2/07/23
CDR Video Conference End

## Part3
The Zenith Program - NASA Student Launch |  |  |  |  | Phase 4 | [36 empty] | PHASE 5
WBS NUMBER | TASK TITLE | START DATE | END DATE | DURATION |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37
[5 empty] | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M
5.1 | FRR Q&A | 2023-02-09 | 2023-02-09 | 0 | bar: R
5.2 | Manufacture Full-Scale Vehicle | 2023-02-10 | 2023-02-25 | 15 | bar: F to 28 F
5.2.1 | Manufacture Payload | 2023-02-10 | 2023-02-25 | 15 | bar: F to 28 F
5.2.2 | Pre-flight Testing | 2023-02-16 | 2023-03-02 | 14 | bar: 27 R to 29 R
5.3 | Vehicle Demonstration Flight | 2023-03-04 | 2023-03-04 | 1 | bar: 29 F
5.3.1 | Vehicle Demonstration Flight Deadline | 2023-03-06 | 2023-03-06 | 0 | bar: 30 M
5.4 | Write FRR Report | 2023-02-16 | 2023-03-02 | 14 | bar: 27 R to 30 M
5.5 | Create FRR Presentation Slides | 2023-02-16 | 2023-03-02 | 14 | bar: 27 R to 30 M
5.5.1 | FRR Report Deadline | 2023-03-06 | 2023-03-06 | 0 | bar: 30 M
5.6 | FRR Video Conference | 2023-03-13 | 2023-03-31 | 18 | bar: 31 M to 33 F
5.7 | Payload Demonstration Flight | 2023-04-01 | 2023-04-01 | 1 | bar: 33 F
5.7.1 | Payload Demonstration Flight Deadline | 2023-04-03 | 2023-04-03 | - | bar: 34 M
6a | Competition | 2023-04-12 | 2023-04-16 | 4
6.1 | Travel to Marshall SFC | 2023-04-12 | 2023-04-12 | 1 | bar: 34 W
6.2 | Launch Readiness Review | 2023-04-13 | 2023-04-14 | 1 | bar: 34 R to 34 F
6.3 | Launch Day | 2023-04-15 | 2023-04-15 | 1 | bar: 34 F
6.3.1 | Backup Launch Day | 2023-04-16 | 2023-04-16 | 1 | bar: 34 F
6b | PLAR | 2023-04-17 | 2023-05-01 | 14
6.4 | Analyze competition flight data | 2023-04-17 | 2023-04-19 | 2 | bar: 35 M to 35 T
6.5 | Write PLAR Report | 2023-04-19 | 2023-04-30 | 11 | bar: 35 W to 36 F
6.5.1 | PLAR Report Deadline | 2023-05-01 | 2023-05-01 | - | bar: 37 M
3/04/23
Full Scale Demo Launch
4/03/23
Payload Demo Deadline
05/01/23
PLAR Deadline
2/9/23
FRR Q.A