## OPPM
Copyright OC Tanner 2007
[5 empty] | Group: 518 |  |  |  | Project: |  | Movement Through Deep Regolith | [10 empty] | Date: | 2026-08-06
Project Objective: Design a novel form of movement that can successfully traverse the lunar surface at the poles
| Objectives |  |  |  |  | Major Tasks |  |  | Project Completed By: May 01, 2022 | [11 empty] | Owner / Priority
| ¢ |  |  |  | 1 | Spring Semester Initial Meeting |  |  | ™ | [13 empty] | ✓
| ¢ |  |  |  | 2 | Spring Semester Work Breakdown Structure |  |  | ™ | [14 empty] | ✓
| ¢ |  |  |  | 3 | Begin CAD of General Design |  |  |  | ™ | [10 empty] | ✓
| ¢ |  |  | ¢ | 4 | Apply for Graduation |  |  |  | ™ | ™ | [9 empty] | A
|  | ¢ |  |  | 5 | Order Parts |  |  |  | ™ | [13 empty] | ✓
[5 empty] | 6 | 3D Print CAD Test Parts |  |  |  |  | ™ | [9 empty] | ✓
| ¢ |  |  |  | 7 | Collect Ordered Parts |  |  |  |  | ™ | [12 empty] | ✓
|  | ¢ |  |  | 8 | Test individual BOM Components |  |  |  |  | ™ | [10 empty] | ✓
|  | ¢ |  |  | 9 | Assemble Prototype | [5 empty] | ™ | [12 empty] | ✓
|  | ¢ |  |  | 10 | Write Initial Code | [5 empty] | ™ | ™ | [8 empty] | ✓
|  | ¢ |  |  | 11 | Test Prototype | [6 empty] | ™ | [7 empty] | ✓
| ¢ |  |  |  | 12 | Update Final Design using Prototype Data | [6 empty] | ™ | [7 empty] | A
| ¢ |  |  |  | 13 | Update Bill of Materials | [6 empty] | ™ | [10 empty] | ✓
| ¢ |  |  |  | 14 | Order Parts | [6 empty] | ™ | [9 empty] | ✓
| ¢ |  |  |  | 15 | Finalize the Design for the Mechanism | [7 empty] | ™ | [6 empty] | ✓
|  | ¢ |  |  | 16 | Submit Final Designs to Machine Shop | [7 empty] | ™ | [6 empty] | ✓
| ¢ |  |  |  | 17 | Collect Ordered Parts | [7 empty] | ™ | [8 empty] | ✓
|  | ¢ |  |  | 18 | Test Updated BOM Components | [7 empty] | ™ | [7 empty] | ✓
|  | ¢ |  |  | 19 | Assemble Final Design | [8 empty] | ™ | [8 empty] | ✓
|  | ¢ |  |  | 20 | Finalize the Code | [7 empty] | ™ | ™ | [9 empty] | ✓
|  | ¢ |  |  | 21 | Begin Testing Mechanism | [7 empty] | ™ | ™ | [7 empty] | ✓
|  | ¢ |  |  | 22 | Begin Debugging Code | [7 empty] | ™ | ™ | [9 empty] | ✓
|  | ¢ |  |  | 23 | Finalize Code | [7 empty] | ™ | ™ | [9 empty] | ✓
|  |  | ¢ |  | 24 | Begin Final Presentation | [8 empty] | ™ | [7 empty] | ✓
|  |  | ¢ |  | 25 | Revise Final Presentation | [9 empty] | ™ | ™ |  |  |  | ✓
|  |  | ¢ |  | 26 | Finish Project Presentation | [10 empty] | ™ | [6 empty] | ✓
| ¢ |  |  |  | 27 | Engineering Day | [11 empty] | ™ |  |  | A
| ¢ |  |  |  | 28 | Finals | [12 empty] | ™ |  | A
| ¢ |  |  | ¢ | 29 | Graduation | [13 empty] | ™ | A
[7 empty] | # People working on the project: | 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| Academics | Testing | Presentation | Graduation |  |  |  |  | 2023-01-09 | 2023-01-13 | 2023-01-18 | 2023-02-02 | 2023-02-16 | 2023-02-27 | 2023-03-11 | 2023-03-18 | 2023-03-25 | 2022-03-31 | 2023-04-01 | 2023-05-06 | Joshua | Enrique | Emily | Andres | Joseph
Millions
[26 empty] | Labels | Budgeted | Expended
[26 empty] | Product Cost | 500 | 0
[26 empty] | Material Cost | 1000 | 0
[26 empty] | Project Cost | 2000 | 0
Waiting to hear about the involvement from Continental in reguards to the brake regeneration and boost.
[10 empty] | Alt + | 152 | 153 | 0162 | 0163 | 0155 | 0165
[10 empty] | Wingdings 2 | ˜ | ™ | ¢ | £ | › | ¥
Major Tasks
Summary & Forecast
Objectives
Target Dates
Costs

## Cost Sheet
| Product Cost |  | Material Cost |  | Project Cost
Description | Budgeted | Expended | Budgeted | Expended | Budgeted | Expended |  |  |  | Salary | 20
| 500 | 0 | 1000 | 0 | 2000 | 0 |  | Millions |  | hours per week | 40
[7 empty] | Labels | Budgeted | Expended | number of weeks | 16
[7 empty] | Product Cost | 500 | 0 | Number of People | 2
[7 empty] | Material Cost | 1000 | 0 | Weight Factor | 1.75
[7 empty] | Project Cost | 2000 | 0 | Cost of Employee | 25600
Note on G3: Shayne McConomy: Cost of Employee
Note on K5: Shaynemcconomy: This is the cost of the product. You will have to calculate the material used rather than purchased

## Sheet1
Driveline Issues & Problems: |  | Today's Date: |  | 2026-08-06
| Issue: |  | How to resolve issue / What is needed: |  | Groups necessary to resolve issue: | Date Problem must be resolved:
1 | Unsure of packaging constraints for front driveline |  | Packaging plans for engine compartment |  | BIW, Engines, Energy Management, Driveline | 2009-09-25
2 | Unsure of packaging constraints for rear driveline |  | Packaging plans for driveshaft tunnel & rear sub-frame area |  | BIW, Engines, Energy Management, Suspensions, Driveline | 2009-09-25
3 | Motor specificatoins are unknown |  | Motor specifications - (We are assuming the TM4) |  | Engines, Driveline | 2009-10-01
4 | Loading parameters are unknown for rear sub-frame |  | Simpack model of rear sub-frame is needed to determine vibration constraints |  | Dr. Venhovens, Driveline | 2009-10-01
5 | Design requirements for wheels & tires are unkown |  | Need input from California School of Design about design requirements |  | Dr. Venhovens, California Design School, Driveline | 2009-10-16
Results / Resolutions:
Issue:
1 | Get in touch with BIW, Maybe using a range extender with the gearbox and generator combined
2 | Get in touch with necessary groups
3 | Assume TM$, but not set in stone
4 | Hopefully by the end of the week
5 | Plan on 17" wheels with Chevy Volt tires from Michelin