## Sheet1
Dates | Milestones | Tasks | Description
2024-01-08 | Classes Begin
2024-01-09 | Finalize Design
Ensure final design meets design requirements
Sponsor check off final design
Learn wire modelling with Creo
Working CAD model
2024-01-14 | Purchase all necessary components
|  | Purchase electronic components | Lasers and Color Sensor
|  | Purchase 3D printing materials | PLA, ABS, PETG, Nylon
2024-01-17 | CAD models for testing fixture & baseplate
Create parts drawings and assembly
|  | Submit baseplate drawing to Danfoss for approval | Baseplate drawings require approval through Danfoss before Manufacturing can begin
2024-01-20 | Simulation operation of system
|  | Have all the parts on CAD finished | Complete CAD files exported as .stp files into the team workspace on MS teams
Full assembly of finalized design with animation
FEA analysis on system supports
2024-01-24 | Purchase of structural materials for testing fixture
|  | Check with vendors to find appropriate pricing | Check with FAMU-FSU to see which vendors they prefer
Submit bill of materials for initial order
2024-01-25 | Updated Prototype
Print all parts required for prototype 2
Assembly parts and finalize electronics
2024-01-26 | VDR4
Ensure prototype is accurate and can perform to need
Finalize presentation and practice as a team
2024-01-27 | Coding of the sensors and stepper motor
Draw state diagram for system
Write code for stepper motor open & close operation
Write code for operation of lasers
Write code for operation of the color sensors
Integrate system operations code and write LCD code
Write code for user interactions
Integrate all code with correct prioritization
Fix any bugs or errors found in code
2024-02-02 | Wiring & pin tracking document
Generate pin tracking schematic
Add pin tracking table with required wire lengths
2024-02-04 | Structural components machined
Communicate drawings with machine shop
Machine shop pending
Pick up parts from machine shop
Test machined parts for potential tolerancing issues
2024-02-18 | Final Design Assembly
|  | All parts manufactured and assembled | Attempt first system assembly with all completed components collected
|  | Have necessary changes made and sent back to machine shop | Make corrections and have them manufactured
Pick up parts from machine shop
Check parts for potential toleracing issues
2024-02-25 | Test of system for functionality
Conduct testing of the assembled system
2023-03-03 | VDR 5
Ensure prototype is accurate and can perform to need
Finalize presentation and practice as a team
2024-03-04 | Spring Break
2024-03-05 | Spring Break
2024-03-06 | Spring Break
2024-03-07 | Spring Break
2024-03-08 | Spring Break
|  | Make necessary corrections to system and retest | Making corrections and reattempting to conduct successful tests
2024-03-10 | Danfoss comes to witness testing
|  | Bruce Barnett (Advisor) will meet to watch testing | Bruce gives input about project to ensure that it's performance meets the needs of Danfoss
2024-03-16 | Finalize Bruce's adjustments
Make possible changes that the customer might want
2024-03-25 | Senior Design Day
|  | Poster and Design done (VDR6) | Create a Poster for senior design day
2024-04-29 | Finals
Study
2024-05-04 | Graduation
Get the Diploma