## Sheet1
Task | Description | Est. Completion Date
Dykem Testing
| Test Dykem's reaction with different materials and test best application method | December 13th
Working CAD Model
| Adjust and optimize a CAD design in accordance with Dykem testing and conclusions Add motion and simulation to the design | Mid January
Add motion and simulation to the design
Site Visit
| Visit JTEKT Cairo plant in order to get another perspective on the location of device with context and understanding to better evaluate conditions, test prototype fit | End of January
Order Materials
| Order materials in order to create the updated prototype from CAD, as well as acquire existing and preferred materials from Sponsor | End of January
VDR4
| Update and prepare VDR information to reflect progress in CAD and physical prototyping | January 26th
Present said information
Assemble Chassis
| Use ordered materials to create our prototype and perform testing, taking note of improvements and possible material replacements | End of Feburary
Poster 2
| Update previous poster to current design and current work | End of Feburary
Also make style corrections from previous T.A. advice
Order Materials
| Use updated material list and requirements to order new materials that will be used to create better prototypes, update budgetary usage | End of Feburary
Work on Electronics
| Use delivered materials to begin higher-fidelity automation, keeping optimization in mind as well as ordering new parts that can assist | Beginning of March
VDR5
| Update and prepare information in accordance with new prototypes, report findings and share future plans from said findings Start Website Design | March 2nd
Spring Break
| Perform minor individual research, take some time away from the project so as to return with fresh insight and energy | Mid March
Finalize Bearing Painter
| Return from Spring Break, assemble final design and optimize, perform last minute maintenance | End of March
Finalize Website
| Finish Website design, ensure no dead links or incorrect pages exist | End of March
Senior Design Day
| Powerpoint and poster presentations | April 1st
Finals
| Final examinations and last week of school | April 29 - May 3
Graduation
| Receive degree and enter the work force! | May 4th